## TestPlan
Test Phase Objectives | Test Approach | Resources | Planned Scheduled | Test Environment & Configurations | Entry Criteria | Exit Criteria | Roles & Responsibilities | Test Case Tracking | Test Defects Tracking | Planned Test Hours
Smoke Testing Regression Testing UAT | 1. Every requirement should be formed as Test case. 2.Test case Review and Approved. 3. RTM should be meet as per he requirement. 4. Automation tool will use : Selenium WebDriver. 5. All QA team will be part of this mission. | 1. Three Manual testers along with 1 Automation tester. | This phase includes key milestone for this test phase. 1. Development of test case. 2. Approval of test case. 3.Preparation of test Environment. 4. Development of Automation test script. 5. Test Execution date. | Environment List: QA, SIT, Staging. This three environment should reday to execute test case | List of criteria should perform before go for actual execution. 1. Test plan approval. 2. Test environment stable and ready. 3. Test Cases witten and approved. 4. Test tool ready. 5. Test resources available. | 1. Every test case execution should complete. 2. Should be less number of severity of Open Defects. | 1. Test Environment Support: Team lead & Support team. 2. Development work: Dev manger & Team 3. Release Manager(Responsible for deploying code and configuratiob changes to the test environment). 4. Approver of test plan: (Name of all approver) | 1. mention status of each test case. 2. % pass and fail of test case. 3. Number of blocker. 4. Link of test management tool. | Add the Defect tracking tool link. | Include number of hours required for test execution.

## Test Case
S.l No | Test case objective | Test Data | Steps | Expected Result | Actual Result | Status | Remark
1 | Launch the Application | URL of the Application: https://www.saucedemo.com/ | 1. Open any browser and use the URL to launch | Application should launch | Application launched successfully | PASS
2 | Verify Login page UI components | Application URL:https://www.saucedemo.com/ | 1. Launch the URL. 2. Check User Name, Password text box and Sign in button. 3. Enter UN and Password. 4. Click on Sign in button. | user should allow to enter User name,Password and click on Sign in button | Working as expected | PASS
3 | Login to application using valid credentails | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. | User should able to login to application | User able to login to application | PASS
4 | Login to application using invalid credentials | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. | User should allow to login to application. | User not able to login | PASS
5 | Login to applivation with out entering user name | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL 2. Keep user name field as blank. 3. Enter password and click on sign in Button | Error message should display | Error message displayed | PASS
6 | Enter the User name and Password character count exceed 50. | URL: https://www.saucedemo.com/ | 1. Launch the URL. 2. Enter the User name and password count length should exceed 50. | application should not allow to enter user name and password that length >50. | Working as expected | PASS
7 | Verify Home page | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Check the Home page components like page title, all item present in home page | User should see all the require component | All the component is displaying in UI | PASS
8 | Check ADD TO CART option | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Choose a item and click on Add to cart button. 4. Click on cart icon present right top of the page. 5. Check the item added to cart. | User should able to see added item in cart | Can see item in cart | PASS
9 | Check the filter option | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Filter the Name from A To Z and filter based on price. | Item should display in UI based on filter | Working as expected | PASS
10 | verify check out option under your cart page | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Choose a item and click on Add to cart button. 4. Click on cart icon present right top of the page. 5. Check the item added to cart. 6. Click on check out button. | Page should navigate for Check out | Working as expected | PASS
11 | Go for Check out with out added any item to cart | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Choose a item and click on Add to cart button. 4. Click on cart icon present right top of the page. 5. Check the item added to cart. 6. Click on check out button. | Error message should display | Error message not displaying | FAIL
12 | Update one item from DB using SQL query andVerify In UI | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Check the newly added item should display in UI | Item should display in UI | Item dislayed in UI | PASS
13 | Delete one item from DB and verify in UI | URL: https://www.saucedemo.com/ UN : standard_user password: secret_sauce12 | 1. Launch the URL. 2. Enter User Name, Password text box and click on Sign in button. 3. Check deleted item should not display in UI | Deleted item should not display. | Deleted item not displayed in UI | PASS